## Bug Report
Defect # | Status | Raised By | Tested on Version | Test Case ID | Steps to reproduce | Test Data | Expected Result | Actual Result | Priority | Severity
D-01 | Closed | Amira Ali | V2 | CO-10 | 1- open the website https://automationexercise.com/ 2-Go to "Products"page 3-Select any product with any quantity 4-Go to "cart"page 5-press on "Proceed to Checkout" 6-press in "Place order" 7-enter any invalid Name | Invalid Name on card | The system should reject an the name and display a message error indcate "Invalid name" | system accepted the invalid name | high | Medium
D-02 | Closed | Amira Ali | V2 | CO-13 | 1- open the website https://automationexercise.com/ 2-Go to "Products"page 3-Select any product with any quantity 4-Go to "cart"page 5-press on "Proceed to Checkout" 6-press in "Place order" 7-enter any invalid card number | Invalid Card Number | The system will reject an invalid card number and display message error indicate " Invalid card number" | system accepted the invalid card number | High | Medium
D-03 | Closed | Amira Ali | v2 | CO-16 | 1- open the website https://automationexercise.com/ 2-Go to "Products"page 3-Select any product with any quantity 4-Go to "cart"page 5-press on "Proceed to Checkout" 6-press in "Place order" 7-enter any invalid CVC | Invalid CVC | The system will reject an invalid CVC and isplay message error indicate " Invalid CVC" | system accepted the invalid CVC | high | Medium
D-04 | Closed | Amira Ali | V2 | CO-19 | 1- open the website https://automationexercise.com/ 2-Go to "Products"page 3-Select any product with any quantity 4-Go to "cart"page 5-press on "Proceed to Checkout" 6-press in "Place order" 7-enter any invalid Expiration | Invalid Expiration | The system will reject an invalid Expiration and isplay message error indicate " Invalid Expiration" | system accepted the invalid Expiration | High | Medium
D-05 | Closed | Amira Ali | V2 | CO-22 | 1- open the website https://automationexercise.com/ 2-Go to "Products"page 3-Select any product with any quantity 4-Go to "cart"page 5-press on "Proceed to Checkout" 6-press in "Place order" 7-enter any invalid Year | Invalid Year | The system will reject an invalid year and isplay message error indicate " Invalid year" | system accepted the invalid year | high | Medium
D-06 | Closed | Amira Ali | V2 | CO-24 | 1- open the website https://automationexercise.com/ 2-Go to "Products"page 3-Select any product with any quantity 4-Go to "cart"page 5-press on "Proceed to Checkout" 6-press in "Place order" 7-check the fields lable is displayed |  | The system should display all payment field labels clearly, correctly | The Payment page displays the Name on Card, Card Number, CVC, and Expiration labels, but the "Year" label is missing. | High | Low
D-07 | Closed | Hanan Mohammed Elhady | V2 | US02 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4- Enter invalid name in Name field 5- press TAB and move to next field | Name : numbers and charcters ======================== Name : special characters and charcters ======================== Name: first character space | System displays error message indicating "Entered data are not allowed" | System accept name field | Low | High
D-08 | Closed | Hanan Mohammed Elhady | V2 | US05 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter Invaild Email Address 5- press TAB and move to next field | Email Address :vaild without domail name¦¦ =============================== Email Address :vaild without characters ¦¦ =============================== Email Address :vaild without numbers ¦¦ =============================== Email Address :vaild and first character has space ¦¦ | System displays error message indicating "Entered data are not allowed" | System accept vaild Email Address without domail name ==================================== System accept vaild Email Address without characters ==================================== System accept vaild Email Address without numbers ==================================== System accept vaild Email Address and first character has space | Low | Medium
D-09 | Closed | Hanan Mohammed Elhady | V2 | US12 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 6-in"Enter Account Information" 7-Enter invaild Name 8- press TAB and move to next field | Name : numbers and charcters ======================== Name : special characters and charcters ======================== Name: first character space | System displays error message indicating "Entered data are not allowed" | System accept name field | Low | Medium
D-10 | Closed | Hanan Mohammed Elhady | V2 | US16 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 6-in"Enter Account Information" 7-Select vaild Day 8- press TAB and move to next field | Day : Select one option of Day successfully | Day selected successfully | System display 31 days in April,June,September,November,February | Medium | Medium
D-11 | Closed | Hanan Mohammed Elhady | V2 | US22 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 6-in"Enter Account Information" 7-Enter invalid Name in First Name field 8- press TAB and move to next field | First Name : numbers and charcters ======================== First Name : special characters and charcters ======================== First Name: space | System displays error message indicating "Entered data are not allowed" | System accept numbers in field ================================ System accept Special character in field ================================ System accept spaces only in field | Low | Medium
D-12 | Closed | Hanan Mohammed Elhady | V2 | US25 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 6-in"Enter Account Information" 7-Enter invalid Name in LastName field 8- press TAB and move to next field | LastName : numbers and charcters ======================== LastName : special characters and charcters ======================== LastName: Lastcharacter space | System displays error message indicating "Entered data are not allowed" | System accept numbers in field ================================ System accept Special character in field ================================ System accept spaces only in field | Low | Medium
D-13 | Closed | Hanan Mohammed Elhady | V2 | US28 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 6-in"Enter Account Information" 7-Enter first name + last name mismatch with Name field 8- press TAB and move to next field | First Name : vaild name Last Name : vaild name (But mismatch to Name field) | System display error indicating "First Name and Last Name mismatch to Name field " | System accept First name and Last Name fields | Low | Low
D-14 | Closed | Hanan Mohammed Elhady | V2 | US31 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 6-in"Enter Account Information" 7-Enter invaild address in Address field 8- press TAB and move to next field | Address : special characters ================================ Address : numbers ================================ Address : space | system display error indicating "Adress must be characters and numbers " | System accept numbers in field ================================ System accept Special character in field ================================ System accept spaces only in field | Low | Medium
D-15 | Closed | Hanan Mohammed Elhady | V2 | US34 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 2 6-in"Enter Account Information" 7-Enter invaild Address 2 in Address 2 field 8- press TAB and move to next field | Address 2 : special characters ================================ Address 2 : numbers ================================ Address 2 : space | system display error indicating "Adress must be characters and numbers " | System accept numbers in field ================================ System accept Special character in field ================================ System accept spaces only in field | Low | Low
D-16 | Closed | Hanan Mohammed Elhady | V2 | US38 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 2 6-in"Enter Account Information" 7-enter characters and spaces in state ,but mismatch with country 8- press TAB and move to next field | state : characters and spaces mismatch with country | System display error indicating "state must be match with country" | System accept state field | Low | Low
D-17 | Closed | Hanan Mohammed Elhady | V2 | US39 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 2 6-in"Enter Account Information" 7-Enter invaild state country 8- press TAB and move to next field | State : special characters ============================= State : Numbers ============================= State :space | system display error indicating "State must be Characters and spaces " | System accept numbers in field ================================ System accept Special character in field ================================ System accept spaces only in field | Low | Medium
D-18 | Closed | Hanan Mohammed Elhady | V2 | US42 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 2 6-in"Enter Account Information" 7-enter characters and spaces in City,but mismatch with State 8- press TAB and move to next field | City: characters and spaces mismatch with State | System display error indicating "Citymust be match with State" | System accept Cityfield | Low | Low
D-19 | Closed | Hanan Mohammed Elhady | V2 | US43 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 2 6-in"Enter Account Information" 7-Enter invaild City 8- press TAB and move to next field | City: special characters ============================= City: Numbers ============================= City:space | system display error indicating "Citymust be Characters and spaces " | System accept numbers in field ================================ System accept Special character in field ================================ System accept spaces only in field | Low | Medium
D-20 | Closed | Hanan Mohammed Elhady | V2 | US46 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 2 6-in"Enter Account Information" 7-Enter invaild Zipcode 8- press TAB and move to next field | Zipcode : 5 digits ========================== Zipcode : 7 digits ========================== Zipcode : characters ========================== Zipcode : Special characers ========================== Zipcode : space | System display error indicating "Zip code must be 6 digits " | System accept 5 digits ============================== System accept 7 digits ============================== System accept characters ============================= System accept special characters ============================= System accept spaces | Medium | Medium
D-21 | Closed | Hanan Mohammed Elhady | V2 | US49 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 2 6-in"Enter Account Information" 7-Enter vaild Mobile Number 8- press TAB and move to next field | Mobile number : start without 010, 011,012,or 015 and 8 digits ==================================== Mobile number : start with vaild prefix and 7 digits ==================================== Mobile number : start with vaild prefix and 9 digits | System display error indicating "Mobile Number must start with vaild prefix and 8 digits" | System accept Mobile Number field | Medium | Medium
D-22 | Closed | Hanan Mohammed Elhady | V2 | US50 | 1- Open website via https://automationexercise.com 2- Click on "Signup/ Login" button 3- in "New User Signup!" 4-Enter vaild name 5-Enter vaild and new Email Address 2 6-in"Enter Account Information" 7-Enter vaild Mobile Number 8- press TAB and move to next field | Mobile number : characters ==================================== Mobile number : spaces ==================================== Mobile number : specail characters | System display error indicating "Mobile Number must start with vaild prefix and 8 digits" | System accept Mobile Number field | Medium | High
D-23 | Closed | Ibrahim Akram | V1 & V2 | L-03 | 1. Go to http://automationexercise.com 2. Click 'Signup / Login' 3. Enter email with leading or trailing space 4. Enter matching password 5. Click 'Login' | Email with leading/trailing space (e.g. ' test@test.com') | The system will show an error message | The system accepted the email with leading/trailing space and showed no error message | Low | Low
D-24 | Closed | Ibrahim Akram | V1 & V2 | L-07 | 1. Go to http://automationexercise.com 2. Click 'Signup / Login' 3. Enter valid email 4. Enter spaces only in the password field 5. Click 'Login' | Password with spaces only (e.g. ' ') | The system will show an error message | The system accepted the password with spaces only and showed no error message | Medium | Medium
D-25 | Closed | Ibrahim Akram | V1 & V2 | L-10 | 1. Go to http://automationexercise.com 2. Click 'Signup / Login' 3. Enter valid email 4. Enter incorrect password 5. Click 'Login' | Valid email and not matching password | The system will show an error message | System logged in successfully with wrong password | Critical | Critical
D-26 | Closed | Ibrahim Akram | V1 & V2 | P-S03 | 1. Go to http://automationexercise.com 2. Click 'Products' 3. Enter '@@@' in search field 4. Click the search icon | "@@@" | No products will be displayed | All products are displayed | Low | Low
D-27 | Deferred | Esraa Mostafa | V1 | S02 | 1- Navigate to url 'http://automationexercise.com' 2- Verify that home page is visible successfully 3- Click 'Cart' button 4- Scroll down to footer 5- Verify text 'SUBSCRIPTION' 6- Enter email address in input and click arrow button | email : dfghjcxvb@dfghj | System displays error message indicating that the email address is invalid and user is NOT subscribed | Verify success message 'You have been successfully subscribed!' is visible | Low | Medium
D-28 | Deferred | Esraa Mostafa | V1 | CU02 | 1- Launch browser 2- Navigate to http://automationexercise.com 3- Click on 'Contact Us' button 4- Verify 'GET IN TOUCH' is visible 5- Leave one required field blank 6- Fill other valid details 7- Click 'Submit' button 8- Verify error message is displayed 9- Repeat for each required field | Blank name : (empty) Blank file :(empty) Blank subject : (empty) Blank message : (empty) | System displays error message indicating that required fields cannot be blank and form is NOT submitted | Success message 'Success! Your details have been submitted successfully.' is visible in both cases | High | High
D-29 | Deferred | Esraa Mostafa | V1 | CU05 | 1- Launch browser 2- Navigate to http://automationexercise.com 3- Click on 'Contact Us' button 4- Verify 'GET IN TOUCH' is visible 5- Enter valid name, subject and message 6- Enter invalid email format 7- Click 'Submit' button 8- Verify error message is displayed | Invalid email : invalidemail@gmail | System displays error message indicating that email format is invalid and form is NOT submitted | Success message 'Success! Your details have been submitted successfully.' is visible in both cases | High | Medium
D-30 | closed | Aya Mohammed | V2 | LO-06 | 1. Navigate to URL 'http://automationexercise.com'. 2. Verify that the Home page is displayed successfully. 3. Click the Logout button repeatedly (3-4 times quickly) | active email matching password | The application should handle repeated logout requests gracefully and redirect the user to the Login without displaying any system error | the system display error page | Medium | Medium